## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled |  | 57.8 days | 5/20/16 8:00 AM | 7/11/16 9:00 AM |  | 0 | Developed on MVC ( Yii / laravel )
1 | Yes | Auto Scheduled | User Module | 14.4 days | 5/20/16 8:00 AM | 6/1/16 9:00 PM |  | 1 | it will handle both admin and public users.
2 | Yes | Auto Scheduled | Login | 3 days | 5/20/16 8:00 AM | 5/24/16 9:00 PM |  | 2 | User login Include :...
3 | Yes | Auto Scheduled | Registration | 3 days | 5/25/16 8:00 AM | 5/27/16 9:00 PM | 2 | 2 | General Site Form Wizard ...
4 | Yes | Auto Scheduled | Admin User CRUD operation | 3 days | 5/30/16 8:00 AM | 6/1/16 9:00 PM | 2,3 | 2 | admin users can be create, update,read and deleted...
5 | Yes | Auto Scheduled | Admin Module | 40.6 days | 6/3/16 3:00 PM | 7/11/16 9:00 AM | 1FS+2d | 1
6 | Yes | Auto Scheduled | Dashboard | 3 days | 6/3/16 3:00 PM | 6/8/16 9:00 AM |  | 2 | Recently added public user profile...
7 | Yes | Auto Scheduled | Permission handling | 3 days | 7/6/16 3:00 PM | 7/11/16 9:00 AM | 6 | 2
8 | Yes | Auto Scheduled | Company Module | 13.4 days | 6/8/16 3:00 PM | 6/21/16 9:00 AM |  | 1
9 | Yes | Auto Scheduled | Add Company | 1 day | 6/8/16 3:00 PM | 6/9/16 9:00 AM | 1FS+1d,6 | 2
10 | Yes | Auto Scheduled | Admin Company CRUD operation | 2 days | 6/9/16 3:00 PM | 6/13/16 9:00 AM | 1FS+1d,6FS+1d,9FS+1d | 2
11 | Yes | Auto Scheduled | Search Companies | 3 days | 6/13/16 3:00 PM | 6/16/16 9:00 AM | 10FS+1d | 2 | company list page...
12 | Yes | Auto Scheduled | Review & Follow | 3 days | 6/16/16 3:00 PM | 6/21/16 9:00 AM | 11FS+1d | 2 | Add Review form and review list below the company detail page....
13 | Yes | Auto Scheduled | Job Module | 16.6 days | 6/21/16 3:00 PM | 7/6/16 9:00 AM | 8 | 1
14 | Yes | Auto Scheduled | Post Job | 4 days | 6/21/16 3:00 PM | 6/27/16 9:00 AM |  | 2 | post job on behalf of company...
15 | Yes | Auto Scheduled | Apply on Job | 4 days | 6/27/16 3:00 PM | 7/1/16 9:00 AM | 14FS+1d | 2
16 | Yes | Auto Scheduled | Short list applicants | 3 days | 7/1/16 3:00 PM | 7/6/16 9:00 AM | 15FS+1d | 2 | short listing applicants by sending their resume links to employer...

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | Windows User Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | Rs 0.00/h | 0
1 | Sadaf | S | Work |  |  |  |  | 100% | Rs 350.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Login | Sadaf | 0 | 15h | 100%
Registration | Sadaf | 0 | 15h | 100%
Admin User CRUD operation | Sadaf | 0 | 15h | 100%
Dashboard | Sadaf | 0 | 15h | 100%
Permission handling | Sadaf | 0 | 15h | 100%
Add Company | Sadaf | 0 | 5h | 100%
Admin Company CRUD operation | Sadaf | 0 | 10h | 100%
Search Companies | Sadaf | 0 | 15h | 100%
Review & Follow | Sadaf | 0 | 15h | 100%
Post Job | Sadaf | 0 | 20h | 100%
Apply on Job | Sadaf | 0 | 20h | 100%
Short list applicants | Sadaf | 0 | 15h | 100%